## Instructions
RFP Pricing Worksheet
Instructions to Vendors
Vendors must complete all pricing tables in this workbook. Pricing shall be fixed-price, all-inclusive, and valid for 180 days. Any assumptions or exclusions must be explicitly stated. Notes: • Enter currency values without commas (formatting is applied). • Use the Deliverables tab to confirm inclusion (Y/N) and provide notes. • Use the Exclusions tab to list anything not included in your fixed price.

## 1_Summary
SECTION 1 — Summary of Total Proposed Pricing
Pricing Component | Fixed Price ($)
Planning & Discovery
UX/UI Design
Application Development
Testing & UAT Support
Deployment & Go-Live
Hypercare / Warranty
TOTAL FIXED PRICE (Build) | 0
Ongoing Costs | Fixed Price ($)
Continuous development/ enhancement aligned to assumptions in 6.2
Application Support (Tier 3+) aligned to 6.3
Testing & UAT Support
Deployment & Go-Live
Hypercare / Warranty
Hosting
TOTAL FIXED PRICE (Build) | 0

## 2_Milestones
SECTION 2 — Milestone-Based Pricing & Payment Schedule
Milestone ID | Phase | Fixed Price ($) | % of Total | Payment Trigger | Planned Start | Planned End | Notes
M1 | Discovery & Requirements |  |  | Deliverables approved
M2 | UX/UI Design |  |  | Design sign-off
M3 | Development Phase 1 |  |  | Feature acceptance
M4 | Development Phase 2 |  |  | Feature acceptance
M5 | Testing & UAT |  |  | UAT sign-off
M6 | Go-Live |  |  | Production deployment
M7 | Hypercare Completion |  |  | Warranty period ends
— | TOTAL | 0 | 0%

## 3_Deliverables
SECTION 3 — Deliverables & Scope Pricing Detail
3.1 Planning & Discovery
Deliverable | Included (Y/N) | Notes / Assumptions
Requirements documentation
Product backlog / user stories
Architecture & solution design
Project plan & roadmap
3.2 UX/UI Design
Deliverable | Included (Y/N) | Notes / Assumptions
Wireframes for all screens
Visual design
Accessibility design (WCAG/ADA)
Usability testing
3.3 Application Development
Deliverable | Included (Y/N) | Notes / Assumptions
Front-end development
Back-end/API development
Database design
Authentication/authorization
Third-party integrations
Logging & error handling
3.4 Testing & Quality Assurance
Deliverable | Included (Y/N) | Notes / Assumptions
Test planning & scripts
Manual functional testing
Automated test cases
Performance testing
Security testing
3.5 Deployment & Launch
Deliverable | Included (Y/N) | Notes / Assumptions
Production deployment
Release management
Rollback plan
Go-live support
3.6 Hypercare / Warranty
Item | Included (Y/N) | Duration | Notes
Defect remediation
SLA response times
Knowledge transfer

## 4_Exclusions
SECTION 4 — Explicit Exclusions (Mandatory)
Excluded Item | Impact if Added | Estimated Add Cost ($) | Estimated Add Time (weeks) | Notes

## 5_Other_Services
SECTION 5 — Optional Services (Priced Separately)
5.1 Maintenance & Support (Post-Launch)
Service Description | Pricing Model | Monthly Cost ($) | Annual Cost ($) | Included in Build? (Y/N) | Notes
Application support | Fixed / Retainer |  | 0
Minor enhancements (Describe) | T&M / Mini-SOW |  | 0
Hosting | Pass-through |  | 0
Monitoring & alerting | Included / Add-on |  | 0

## 6_Assumptions
SECTION 6 — Pricing Assumptions (Required)
Vendors must explicitly state assumptions and the impact if invalid.
Assumption | Value/Description | Impact if Invalid | Estimated Add Cost ($) | Notes

## 7_Risks
SECTION 7 — Cost Certainty & Risk Disclosure
Risk Area | Identified (Y/N) | Mitigation Strategy | Residual Risk | Notes
Integration complexity
Data quality
Third-party dependencies
Schedule risk

## 8_Cloud Costs
SECTION 8 — Cloud Costs (Based on Volume Assumptions in 9.2)
Pricing Component | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Notes
Compute
Storage
Data Transfer
Monitoring/ Logging
Security Services
Other (Describe)
TOTAL FIXED PRICE | 0 | 0 | 0 | 0 | 0

## 9_Rate Card
SECTION 9 — Labor Rates
Enter estimated hours for evaluation and for sizing the NTE ceiling. Labor Cost calculates automatically.
Role | Rate (USD/hr) | Minimum Hourly Increments | Notes

## 10_Certification
SECTION 10 — Pricing Certification
By submitting this worksheet, Vendor certifies that pricing is complete, accurate, and inclusive of all required deliverables.
Name | Title | Signature | Date